## Slide 1
NDMC
Data Analytical Visualization Team
Where data comes to
W E L C O M E
life!

## Slide 2
Chart: 
3 Months Evaluation
6 Months Evaluation
9 Months

## Slide 3
3 Months - DA
Childhood Mortality Estimation, Using short-time-period and calendar-year-based estimation
01
Child Health
02
Fertility Rate
03
High risk fertility behavior
04
Perinatal Mortality Rate
05

## Slide 4
3 Months - DA
Covid-19 Modelling
06
Simple Model
Advanced Models
The impact of NPI’s on TC,
CC, ICU and
Death
Many Evidences
were
Communicated

## Slide 5
Performance
All analytical works have been completed successfully
100%

## Slide 6: 3 Months - VP
Comparing and presenting diseases and risk factors pattern and trend
Examining, comparing, and presenting various causes of death and mortality rates for national and regional
Infectious disease real-time modelling and real-time presenting the impact of intervention policies in disease mitigation
Tracking SDG and HSTP-II Indicators for assessing the countries attainment

## Slide 7
3 Months - VP
Visualization of almost 85% of analysed results were complete
01
The interface design was not interactive, expandable, maintainable, re-usable and consistent
02
The database design was not complete, and did not align with the output results
03
It was maintained locally
04

## Slide 8
Performance
With respect to our defined objective we were at:
1%

## Slide 9
Lets Look a head, now!

## Slide 10
6 Months Plan- Evaluation O-01
Digitization of routine activities of the data analytics ad visualization team and other case teams. Developing a central, easy to use and publicly accessible platform for quantifying and interactively presenting most common burden of disease at national and sub-national level. Moreover, implementing and deploying the basic ideology of real time disease modelling for real time decision making. Developing central DB for viz modules.
01
Expected results : Web-based applications and guidelines for the platforms

## Slide 11
Digitization
Covid-19
In depth analysis of CMD and SD, and modelling to forecast and estimate the disease progressions
NBD
Wider content and interactive representations
NHDx
Data for All!
RTDS and NDMC
Web
GESHIARO/Malaria
With: GP/M
EHeRAMS
With: Resilience
ERP
E.P.P
Advanced python based EDHS data analyzer and result generator

## Slide 12: Digitization
3 Months | Interface | Scope | Overall Progress
Continuing in development of NBD automated platform | 90% | 20% (2 out of 7 topics) | 70%
RTDS page betterment and deployment | 70% | From DRGT | From DRGT
Real-time covid-19 modelling | 95% | 65% | 75%
E.R.P | - | - | 40%
Others | - | - | Eherams- 35% Gashiero- 10% MDCTKAD- 85%

## Slide 13
6 Months Plan- Evaluation O-02
Providing Python package code for the selected EDHS Program indicators listed in the Guide to EDHS Statistic.
02
Expected results : Python packages and documentations
Planned | Overall progress
5 analytical topics | 2 completed (40%)

## Slide 14: Data Analysis
Topics | Activities | Overall Progress
Study, analyse and estimate the effects of family planning child mortality in Ethiopia | Inferential and predictive analysis of FP indicators for Child mortality | 80%
Study, analyse and estimate the fertility rate of women in Ethiopia | ASFR TFR GFR | 100%
Study on coverage of vaccination and immunization in Ethiopia | Trends in vaccination coverage | 100%
Malaria prevalence and the impact of its intervention on reducing under-five mortality | Trends in malaria prevalence trends Nets, insecticide, and anti-malaria drugs | 40%

## Slide 15: Data Analysis – con…
Topics | Activities | Overall Progress
Nutritional status and associated factors among children under age five | Anthropometric assessment Infant and young child feeding practices Diversity of foods fed, and frequency of feeding | 40%
Maternal health care seeking behaviour | MNC service coverage and utilization of the health care system | 60%
Assessing knowledge and awareness of HIV/AIDS, related to its prevalence | Prevalence, K and A | 67%

## Slide 16
6 Months Plan-
Evaluation
O-08 and O-09
Applying Data Science to solve at least one health sector challenges
02
Expected results : Evidence briefs and methodological papers
Planned | Overall progress
Assessment of SDG and HSTP-II | Discussion is underway with abroad and local experts

## Slide 17
6 Months Plan-
Evaluation
O-10 – World Bank Project
Capacitate the effective utilization and use of health data at both continental and regional levels through application of health data science
10
Expected results : Training materials and enabled trainees
Planned | Overall progress
Please refer to WB project timeline | 3 out of 12 course materials developed

## Slide 18
6 Months Plan-
Evaluation
O-11 – Capacity Builder (Gemachu)
Increasing the Teams capacity through various intensive trainings
10
Expected results : Training completion certificates
Planned – 3 Months | Overall progress
Training on systematic review | EGT and CB are on discussion
GIS (ArcGIS) – Risk mapping and temporal predictions | New GIS experts and CB are on discussion

## Slide 19
Other Activities
4 Evidence Briefs
Interoperability
01
02
03
04
3 Abstract submission
04
EWARS

## Slide 20
Activity Analysis
and Challenges
We were able widen our scope of health data analysis and achieve more
01
NBD and Covid-19 platforms are now at more stable and interactive version
02
We were able to collaborate with various local and international contributors and collaborators
03
There is still a gap in defining profound research question and identifying indicators for certain diseases or mortality – Low inter-case team collaboration
04

## Slide 21
What's Next?

## Slide 22
Completing planned yet incomplete analytical works.
A-01
Visually enriching and enhancing the visualization hub, by collecting comments from local and international experts
V-02
To model advanced under-five mortality rate estimation
A-03
Include more indicators or re-shape existing indicators for U5-MR and NN-MR, and apply DS concepts to identify significance of these parameters and to forecast
A-04

## Slide 23
Automated Result submission for viz modules
V-05
National health data exchange platform – Analysed Data catalog
V-06
NDMC website localization and interface enhancement
V-07
Completing a dynamic and real-time design of Covid-19
V-08
Trade-off between NP intervention and vaccine intervention
A/V-09

## Slide 24
Automating Health-Atlas – with BoD
V-09
Basics and advanced health data science face-to-face and online training material will be partially completed/ accredited
D-10
A work on EWAR will be started – Malaria Outbreak prediction and impact mitigation
O-11
E.R.P assessment will be completed and at least one EPHI center’s work will be automated (HR or Finance)
V-12
Others PPE, Sero and Grant management unit dashboards – work guideline, requirement and framework : part of E.R.P or RTDS
V-13

## Slide 25: New staffs
EPHI compound climate statistics from 1980 - 2018
Validating climate parameters indexes, and developing predictive models for malaria outbreak – Fistum will lead EWAR
Modeling impact of climate factors on seasonal diseases
Creating dynamic and interactive maps and integrating with NDMC portal
Mapping BOD at Woreda level
Mapping malaria risk areas
Prepare manual for GIS Introductory training
Viral load, 2030 count down analysis, and covid-19 modelling

## Slide 26
T H A N K S